## Sheet1
2010 Hooding Ceremony and Graduation
Tracking Spreadsheet
| WHO | $ NEEDED |  |  | KEY | Task
WHAT | DOES IT | ? | Amount | Org | FACTS | # | TASKS | DATE | CONTACT PERSON | EMAIL | PHONE | COMMENTS POST EVENT
Date & Time | n/a |  |  |  | Fri 6/11/10; 10-12noon latest followed by MPA Alum Assn reception; doors at 9:30 | 1 | Set date and time | DONE
Location: Room Reservation | Randee |  |  |  | Longhouse | 1 |  | DONE
Meet to set/review tasks | Randee/Gail |  |  |  |  | 1 | Review task list; determine/confirm who does what | 2010-05-05
Room/Site Setup | Gail | x |  |  | Check-in: 4 tables in wide part of lobby downstairs | 1 | contact Facilities re: doing work order
[6 empty] | 2 | meet & go to Longhouse to plan site setup
Room: Sound | Gail | x |  |  |  | 1 | contact/meet with Diana to plan sound setup |  | Diana Schlesselman, Electronic Media | dianas@evergreen.edu | 867-6268
Food: Order & PO | Maggie | x |  | split bet MES 25101 (1/3) & MPA 91111 (2/3s) |  | 1
Asking Les & Ken | Randee |  |  |  |  | 1 | emailed their assts; it's on their calendars | DONE
Main Speaker | MES |  |  |  | Gerardo Chin-Leo | 1 | Added to program info | 2010-05-05
MPA Student Speakers | Randee/Maggie |  |  |  | Grady Smith MPA gen; Dylan Dressler MPA Tri | 1 | Email cohorts re: info about speaking and deadline. | done
[6 empty] | 2 | TBD by each cohort by 5/3/10 | 5/3/10 DONE
3
4
5
Program: Order & PO | Randee/Jan coord; Tricia creates | x |  | split bet MES 25101 (1/3) & MPA 25220 (2/3s) | 450; files to them M 4/24/10; they deliver Th 6/3/10 | 1 | Jan got printing estimate | 2010-04-08 |  |  |  | will need more (300?) in even years, when Tribal cohort graduates
[6 empty] | 4 | Given printer deadline, set deadlines for program input; email JT, Randee
[6 empty] | 5 | Edit program; give to Tricia by 5/14/09: prep lists (grad, faculty, staff names), other program info in Word
[6 empty] | 6 | Tricia preps program
[6 empty] | 7 | Jan sends final to Tumwater Printing
[6 empty] | 8 | Jan proofs and selects cover stock
[6 empty] | 9 | Printer sends final proof; Jan reviews/approves
[6 empty] | 10 | Delivery | 2010-06-03
Ceremony Flow | Randee |  |  |  | For program | 1 | emailed draft to Cheryl and Martha for review | 2010-05-03
[6 empty] | 2 | emailed reminder to all to get stuff in | 2010-05-18
[6 empty] | 2 | update program file in Word & email Tricia | 2010-05-18
3
Graduation info & reminders to MPA students | Randee |  |  |  | For program | 1 | email comprehensive grad email
List of MPA graduates | Randee |  |  |  | For program | 1 | Finalize list of graduates for program
[6 empty] | 2 | list of grads who've applied from Elaine
[6 empty] | 3 | Email grads to doublecheck their names
[6 empty] | 4 | Finalize, alphabetize and send to Tricia for program | 2010-05-18
Ushers | Randee |  |  |  | 4 needed for each program | 1 | determine tasks & # needed | done
| Gail |  |  |  |  | 2 | email mpa-all to ask | done
[6 empty] | 3 | MPA ushers: Laura Coghlan, Lori Klatt (til 11), Amadou Ba, Alicia LeDuc, Tribal student
[6 empty] | 4 | email ushers Tues 6/8 to confirm
5
Photos | Maggie |  |  |  | photog to take photo as grad is hooded + group shots | 1 | email Gradtrak to confirm | 2010-05-13
[6 empty] | 2 | get spreadsheets with MES and MPA and MPA tribal grad contact info, email info to GradTrak
[6 empty] | 3 | meet with GradTrak staff b4 Ceremony re: photo setup & procedure
4
5
6
[6 empty] | 7 |  | 2009-06-12
Music | Gail/ Tricia |  |  |  | no $ therefore want recorded (CD) music b4 and after ceremony | 1 | determine music selections, how music/audio works in Longhouse, who will coordinate that day |  |  |  |  | music worked well; began playing at 8:45
[6 empty] | 2 | Tricia got CD
[6 empty] | 3 | Bring music to event
Decorations/Flowers | Randee/Jan | x |  |  | Flowers only -- 2 arrangemnts: 1 lg (in front of podium) & 1 sm (vase upstairs) = $200 approx | 1 | Determine minimum decorations to make it look nice and how we'll get them ($ and/or borrow) | DONE |  |  |  | flowers beautiful, on time; use this vendor again
[6 empty] | 2 | Randee got estimates, spoke with Lorri to confirm that we could pay for flowers using state funds, ordered from Newberry Bay ($182 for 2 arrangements, Jan did PO,
Gift | MPA | x |  | split bet. MPA Initiative (25220) & MES | no gift | 1 | MPA: will be discussed at April fac/staff meeting | done
[6 empty] | 2 | MPA: decision at 5/10 fac/staff -- no gift | 2010-05-10
Regalia for students to borrow | Randee |  |  |  | MPA: 2 hoods that students can share | 1 | MPA: will be discussed at 4/27 fac/staff meeting | 4/27/09 DONE
[6 empty] | 2 | 1 student ended up using
Signs | Randee |  |  |  | 2 signs, 1 on way to Longhouse, 1 at bus loop | 1 | Spoke with Shannon and John to see if Comm bldg signs available; Nope :-(
[6 empty] | 2 | Referred to Ahoi and Bob Worley -- Bob does all graduation signs and MPA/MES never been part of this
[6 empty] | 3 | Spoke with Bob: they will make and put up 3 signs
[6 empty] | 4 | Sent sign instructions to Bob; can only do 2 signs
Last details meeting | All | [5 empty] | Final meeting during week of graduation | did not happen

## Sheet2
Supplies to take
AV Cart from Lab 1 1st floor
Tape
Signs
Blank paper (to improv signs)
Pens
Marking pens
Programs
MPA & MES Hoods + mortar boards
Check in cards
MPA tablecloth
Music CD
Post its
room set up diagram
contact info for key people
check-in list for volunteers
Randee's graduation folder
CK cards
Ck and receipt (from home)
Copy of this spreadsheet
Copy of script
Staff
Randee | 7:15am | Overall MPA
Gail |  | Setup, overall MES
Maggie |  | Catering, photos, overall MPA Tribal
Jan | 8:30am | check in, flowers
Amadou Ba | 9:15 | MPA usher
Alicia LeDuc | 9:15 | MPA usher
Laura Coghlan | 9:15 | MPA usher
Lori Klatt | 9:15 | MPA usher til 11
Tribal student volunteer w/Maggie | 9:15 | MPA usher

## Sheet3
Tasks by Time
Th 6/11 | 1 day before
Get cart; load to bring stuff
Visit Longhouse
| Usher confirming email | done Wed 6/9
Hood borrower confirming email
| Podium & flower pedestals | done Thurs 6/10
Fr 6/12 | THE Day | Police Services x6832 (if doors locked, etc)
When | What | Who | How (supplies/instructions)
7:15am | Randee/Gail get in, get cart from Lab 1, go to Longhouse
7:30 | Check Longhouse set up, reserve seats for cohort & in front row, determine set up of chairs in front for faculty or onstage, podium set up and on-stage hooding procedure -- onstage will only happen if stairs are on both sides, otherwise on floor hooding | Gail/Randee
Maggie get there
8 | Photog get there -- sit in front row | Maggie
8:30 | Jan get there -- set up check in table; Use a program to check grads off as they arrive
8:30 | Sound get there, begin sound check | Gail | Diana x6268
| Music confirm -- CD to sound people | Gail | play music 9 -- ceremony beginning at 10; then when ceremony ends
8:45 | Doug Webb arrive for sound check
8:45 | Catering arrive to set up | Maggie | Kitchen x5275
8:45 | Flowers -- pick up at curb; arrange | Jan | take cart & check from Randee; Lena cell 402-5571
8:45 | Check in table set up/running | Maggie
9am | Start music | Gail
9:15 | Ushers get there | Leslie, Lori, April | tell them where other Hooding Ceremonies are -- MIT/MEd in CRC, etc
9:30 | Doors open
9:50 | Hood to first person (Will Bennett) | Randee
9:55 | Les and Don there? | Randee | Les/Susan x6100; Don/Linda x6400
9:55 | Charlie Teske there -- can get onstage?
10:00 | Ceremony to begin: Stop music when Martha to speak | Gail cue
Hood back from last person (Jason?)
M 6/14 | Take cart & stuff back to Lab 1
by T 6/15 | Take box and fabric back to Comm