Morning

- Adam works on getting artifacts and t-shirts

- Gail works on nametags

12pm

- Quick check-in meeting with TEDx planning team; t-shirt handout (Gail has most recent list)

12:15

- Scott, Irene and Gail meet in E lobby to get area set up and ready (decide where exhibitor and food tables will go)

- Carolyn brings the goods (or doorstoppers) sometime between now and 2pm

- Facilities possibly arrives to help with furniture moving, door opening, and carpet placing

12:30pm

- lunch with speakers in E1105

- tech run through

2pm

- set up registration

- post signage

2:30pm

- first wave of volunteers arrive – send them to Gail

- MC and first speaker mic’d; other speakers for A session ready to go

- Registration ready

- Exhibitors arrive

2:55pm

- Room ambassadors get everyone into their assigned rooms

3pm

- Session A starts

3:30pm

- Food shows up - Gail or Adam supervises?

4:50pm

- Intermission in E lobby

- Session B registration

- Second wave of volunteers arrive – send to Gail

5:10pm

- Session B starts

6:30pm

- Food ready at around this time – Gail or Adam supervises?

7pm

- Reception – all doors open + people can mill about outside the front entrance, as it’s covered

- 2 volunteers needed to help the Undriving table

8pm

- Clean up!!