## Scope
Needs Assessment Notes on Scope
Averi Azar and Mike Ruth, 12 Jan 2021 |  |  | Mindmap of Best Practices, Generally, for Needs Assessment
In Scope (for Reporting in March 2021) | Priority
Stakeholder: Students | 1 | Understand needs of students at key stages of interaction with the graduate programs.
Organize inquiry about "points of articulation" in the entirety of student experience.
Examples: What works well (or badly) for students as they transition from applicant to accepted student status.
Stakeholder: Faculty and Staff | 2 | There are several other "transitions" which strain students through the course of their time in MES.
Understand how faculty and staff also have needs for support at the same "points of articulation"
How do Fac and Staff respond to student needs at these transitions.
What do Fac and Staff do well (or badly) in responding to student needs in these transitions.
Out of Scope (for now)
Stakeholder: Hiring Agencies | 3 | Needs of public (statem local government) stakeholders in hiring, mentoring, interacting with students.
Needs of tribal agencies
Staeholder: Tribal Agencies | 4
Stakeholder: Alumni | 4 | Needs of Alumni
Needs Assessment Process Notes
Use Best-Practices | 1 | Start with a plan. Follow general best-practice for Needs Assessment professional practice
Implement TEAMS or other engagement tools | 2 | Reduce reliance on meetings. Establish and use methods for asynchronous input and discussion
Budget time and effort expectations | 3 | Be realistic about resource constraints (fac/staff time) in relation to tight deadline
Prioritize stakeholders | 4 | Accept that "phasing" is likely. After the initial deadline, further needs will be uncovered for later consideration. Lower priority stakeholders will be brought into the process.
Succinctness | 5 | Try to keep documents short, emphasize graphics over narrative (when under tight timeframe). Make exhibits easy to read and respond to quickly. Agility

## ArticulationPoints
Notes from whiteboard (Averi and Mike, 12 Jan 2021)
Scope Item | 1 | What works well (or badly) for students at key transitions between phases of graduate experience.
| 2 | What works well (or badly) for Faculty and Staff in responding to student needs at these points of articulation.
|  | Student Needs | Grad Student Experience Phase | Faculty Response/Needs | Staff Response/Needs
|  | Students need reliable communication of their application status | ADMISSIONS
|  | Students need more contact and advising | ADMITTED, NOT STARTED | Faculty need to provide advice on course of study | AD heavy workload for individual student communications
|  | How do students feel confident they are set up for success? |  |  | Reliable communication of details for financial aid, registration, tech awareness (computers, I.T., support, etc)
|  | Students are anxious about what 'standards' they are being held to | START OF PROGRAM | How to communicate general expectations at start of program? | AD: Program support (activities)
|  | Need help becoming confident with Canvas, my.evergreen, tech support, other new content systems |  | Backfilling missing undergrad skills
|  | Building a community of learning with cohort |  | Improving writing, quantitative skills (statistics, excel, etc)
|  | Students feel unadvised on how courses work together to build capacity | ADVISING | Adademic advising, informal and unbudgeted effort
|  | Students lack awareness of how to transition to professional life after MES |  | Career advising is not strong skillset of many faculty