## Project Planner
Cowdrey Thesis Project Timeline - Oct 2020 to June 2021
[5 empty] | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Image processing - orthomosaicing | 1 | 16 | 1 | 10 | 0%
Image processing - classification | 9 | 13 | 9 | 1 | 0%
Image processing - statistical analysis | 12 | 11 | 0 |  | 0%
Image processing - mapping of results, look for trends | 14 | 10 | 0 |  | 0%
0%
Case Studies - prospectus | 1 | 10 | 1 | 11 | 0%
Final signed prospectus due to MES Director on 12/11/2020
Case Studies - literature review | 3 | 8 | 4 | 7 | 0%
Case Studies - poster | 7 | 3 | 8 | 2 | 0%
0%
Writing - literature review (continue/revise) | 11 | 9 |  |  | 0%
Writing - methods | 17 | 6 |  |  | 0%
Writing - introduction | 19 | 5 |  |  | 0%
Writing - results | 20 | 6 |  |  | 0%
Writing - discussion/conclusion | 21 | 5 |  |  | 0%
0%
Final thesis - first draft | 14 | 12 |  |  | 0%
Complete first draft due to Erin by 4/9/2021
Final thesis - revisions | 26 | 7 |  |  | 0%
Final thesis - presentation | 29 | 4 |  |  | 0%
Request to present thesis research project during Spring Quarter '21
Present week 8-9: May 18-20 or 25-27
Final thesis - complete | 32 | 2 |  |  | 0%
Final draft of thesis due to Erin by 5/28/2021 |  |  |  |  | 0%
Final signed off version due to MES Office by 6/4/2021 |  |  |  |  | 0%
0%
0%
0%
0%
0%