- MIT ON TACOMA CAMPUS: A Proposal

Diversity and poverty in the classroom often shock beginning teachers who have not had significant experience with them.  Careening from crisis to crisis and exhausted under the load, inexperienced teachers stumble through that first year’s on-the-job training in disappointment and frustration.  The state’s goals for improving education include increasing the percentage of teachers of color and educating teacher candidates from all backgrounds to serve effectively in diverse and/or economically challenged student populations.  This challenge is congruent with Evergreen’s institutional mission, foci and expectations and one that the college already has a good reputation for meeting.  Many potential teacher education candidates concerned about these issues are searching for an affordable teacher education program offered Most of these students need opportunities for evenings/weekends offerings because of work and family obligations, and Evergreen’s MIT program has experience offering those opportunities at Tacoma for an underserved, diverse population.  The MIT program proposes mounting a two-year cohort in Tacoma every three years, overlapping an MIT cohort on the Olympia campus.  MIT on the Tacoma campus would serve an underserved population in a field of high demand within the state and would (could?) increase the overall MIT enrollment.

Why MIT at Tacoma campus?

- Tacoma faculty and students have expressed an interest

- MIT hasn’t offered an evening/weekend program since the popular 2002-04 cohort

- MIT hasn’t offered a cohort on the Tacoma campus since 1994-1996. When the feasibility of a 2+2+1 certification program at Tacoma was examined in fall 2006, it was concluded that the need was compelling and it fit Evegreen Tacoma’s mission.

- MIT supports the Tacoma campus’ emphasis on equity and on serving the community

- MIT commits to placing student teachers in diverse, urban school settings and seeks to strengthen relationships with Tacoma public schools

- 34% of K12 students in Washington are students of color; only 7% of the teachers are people of color

- The percentage of students of color continues to increase, but the percentage of teachers of color remains static

- Projections suggest that children of color will be the majority, representing over 57% of the student population, by 2050 (U.S. Department of Commerce, 1996).

- 31% of Indian students, 25% of Hispanic students, and 23% of Black students met standards on the 2007 10th grade math WASL compared to 58% of Caucasian and 60% of Asian students

- 38% of public school students live in poverty, and the majority of their teachers have little personal experience of poverty

- It’s the right thing to do

Why would students choose MIT at Evergreen Tacoma over UW Tacoma?

  - Evergreen Tacoma has a long, proud history of outreach and hospitality to non-traditional, urban, older students and to students of color.

  - MIT focuses on developing teachers who can be leaders in anti-bias, multicultural education.  The program addresses issues of social justice, equity, and multiple perspectives throughout the two year cohort.  UW Tacoma does not offer this focus.

  - MIT uses an inter-disciplinary model, a strong Evergreen value and effective pedagogy; UW Tacoma is course-based.

  - MIT offers more endorsements; specifically, UW Tacoma does not offer the separate middle level math and middle level science endorsements which are needed in the Tacoma area schools (as indicated in the supply/demand report for ESD 121 showing these are considerable shortage areas). Nor do they offer endorsements in bilingual education, the arts, mathematics, chemistry, physics, or world languages.

  - MIT will offer test-taking workshops and tutorials in writing and math to help applicants pass their WEST B and WEST E tests.  UW Tacoma apparently makes no special effort to support students in preparing for those important exams.  In addition, MIT offers workshops in the art of seminar for students unfamiliar with that important piece of Evergreen pedagogy.

  - When MIT candidates graduate, they have a master’s degree plus 45 hours of work of 96 credits, with many districts hiring our graduates in on the pay scale of master’s degree plus 45 credits. Thus, They enter the system at a higher pay grade than a graduate from UW Tacoma, where graduates are recommended for certification after four to five quarters of study and then must take additional classes to finish the master’s degree.

  - Evergreen’s MIT placement rate has been averaging 20% higher than UW-T’s placement rate ( 85% vs. 65% for 2006 per OSPI data).

A PEW Grant supported the previous MIT cohort at Tacoma—what did we learn?

  - We need to hire a full-time, outreach person for 5 years who is highly effective at:

making personal contacts with prospective applicants, including people currently working as para-professionals in schools, and Tacoma campus current students and graduates, and community members with bachelor’s degrees to determine their interests and readiness for the program in terms of endorsement work and readiness to take and pass the WEST B and WEST E

staying attuned to Tacoma communities and working with Black, Indian, and Hispanic adults; teachers of these ethnicities have the lowest representation in public schools.

providing information about the program

helping applicants clarify career goals – do they really want to be teachers and why?

encouraging applicants; helping them plan the coursework they need; supporting them in preparing for and arranging to take required tests; and helping them problem-solve issues related to childcare and income during the program

setting up appointments for current and former Evergreen students with MIT advising and certification specialist Maggie Foran for transcript analyses and advice about needed coursework

contacting Tacoma Community College, Green River Community College, and Pierce Community College and coordinating with their AA in Education program to determine who might be interested in entering the Tacoma program and then continuing into MIT – create interest and connection for the students

contacting other community colleges in the area and arranging advising sessions with freshmen and sophomores to make sure that they take appropriate writing, math, and science classes before moving over to Tacoma as juniors

coordinating with the Bridge program to ensure that prerequisite work in writing, math, social studies, and science is being addressed in such a way that appropriate credits are offered and WEST B can be passed

developing a report in spring 2010 indicating how many people could reasonably be expected to enter the 2011 cohort with their West B and West E tests taken and passed;

working with MIT field placement specialist Loren Petty to identify and make connections with master teachers who could work with us for practicum and student teaching placements once the MIT program begins.

conducting test preparation workshops

- Time needs to be made available for team planning both before the program begins and as it progresses, and for on-going program assessment during the program.

- Funds need to be available to support a workshop for public school mentor teachers before the beginning of student teaching.

What needs to be accomplished to mount the program in 2011?

- Fall 2008 - Hire an outreach coordinator to start work this fall quarter and continue through spring 2013.  See above for out-reach responsibilities.

- Fall 2008 through the life of the program - Tacoma faculty work with each other and with the Washington Center to ensure that proposed programs address the competencies embedded in the Washington State endorsements for middle level math and middle level science as well as the writing and critical thinking skills required in a masters program. Not all prospective applicants will want these endorsements, so the faculty should become familiar with other potential endorsement areas in order to support students’ work and planning.

- In addition to academic work, potential MIT applicants should have opportunities to work in public school classrooms in order to confirm their interest in teaching and to fulfill MIT program requirements.

- Fall 2008, 2009, 2010 -- MIT alumni panels offer presentations on the Tacoma campus about their experiences in the MIT program and as teachers.

- Fall 2008 through Spring 2011 – Offer appropriate endorsement work within the Tacoma program and/or ensure that prospective applicants are taking appropriate classes at community colleges or on the Olympia campus (during summers).

- Fall 2008 through Fall 2010 – Arrange for prospective students to meet with Maggie Foran for transcript analyses and advice about necessary course-work.

- Winter Quarter 2009 through Winter Quarter 2010 - Arrange for test preparation workshops to be offered to Tacoma campus students and any other prospective MIT applicants for the 2011 cohort.  These workshops need to be substantive, offered in a sequence, and cumulative in their content – not one-shot events.

- Spring 2009 - Ideally, all applicants to whom we have access would take the WEST B Spring 2009, BEFORE entering the Tacoma program in fall of 2009.  If the applicants have already graduated from Tacoma or elsewhere, or are currently in the Tacoma program, they would still be encouraged to take the WEST B next spring.

- Late Spring 2009 through Winter 2010 - Based on WEST B results, and students’ work within the Tacoma program and Bridge program, offer writing and math workshops or tutoring sessions either within the Tacoma program or as extras to support development of critical reasoning and expository writing skills and necessary math concepts and skills.

- Summer 2009 through Winter 2010 – Begin and continue an advertising campaign in newspapers, on the radio, and through appropriate community venues.

- Winter 2010 – Prospective applicants Re-take the WEST B if didn’t pass the first time.

- Winter 2011 – Prospective applicants would take the WEST E. If students did not pass the WEST E, faculty need to be prepared to offer supplementary support before a re-take of the test.

- Students would participate in workshops offered by MIT staff during Winter 2011 on preparing their applications for the program and on how to participate effectively in an Evergreen seminar.  Applications would be due by the end of winter quarter.

Success of an MIT program at the Tacoma campus depends upon the college providing:

- One FTE for a recruiter/advisor to support:

- Two evening/weekend cohorts every six years on a:

- 3-year cycle for the Tacoma program of two years on, one off, beginning in fall 2011 with very strong:

- Institutional commitment to the MIT Tacoma program and to its support of the college mission

- Tacoma administration, faculty and staff commitment of ongoing curricular support and space.