Phase 1 WEST-E Test Development Milestones (Fields in Test Development Groups 1 & 2)

Draft December 21, 2007

| Activity | Tentative Timeframe |
| --- | --- |
| COMMITTEE ESTABLISHMENT |  |
| PESB and Pearson establish Fairness Review Committee and Content Advisory Committees | COMPLETE |
| PRELIMINARY TEST FRAMEWORK REVIEWS (by Mail & Phone) |  |
| Preliminary Test Framework Reviews (OSPI staff & IHE reps) | COMPLETE |
| TEST DEVELOPMENT CONFERENCES |  |
| Conduct Test Development Conferences (Fairness Review & Content Advisory Committees; OSPI staff as observers) | COMPLETE |
| Conduct follow-up committee meetings | January 18, 2008 |
| CONTENT VALIDATION SURVEY |  |
| Distribute surveys | February 2008 |
| Follow-up with survey recipients | March – April 2008 |
| Complete survey data analysis/finalize Test Frameworks | May 2008 |
| PILOT TEST |  |
| Draft/send site recruitment mailing | January 2008 |
| Conduct follow-up with site contacts | February – March 2008 |
| Conduct pilot test | March – April 2008 |
| Complete pilot test data analysis/finalize Test Items | May 2008 |
| Blueprint first test forms | June 2008 |
| STUDY GUIDES/PRACTICE TESTS |  |
| Distribute study guides/practice tests | June 2008 |
| VALIDITY VERIFICATION/STANDARD SETTING |  |
| Conduct first test administration | September 2008 |
| Conduct Validity Verification/ Standard Setting Conference (Passing Score Panels) | October 2008 |
| PESB establishes performance standards | November 2008 |
| Score reports sent/posted | December 2008 |

Test Development Group 1

Test Development Conference –October 29-November 2, 2007

| Test Field Code | Test Field Name |
| --- | --- |
| 020 | English Language Arts |
| 022 | Biology |
| 024 | Earth and Space Science |
| 025 | Physics |
| 029 | Heath/Fitness |
| 031 | Dance |
| 032 | Theatre Arts |
| 033 | Visual Arts |
| 034 | Music: General |
| 035 | Music: Choral |
| 036 | Music: Instrumental |
| 072 | Deaf Education |

Test Development Group 2

Test Development Conference –November 26 -30, 2007

| Test Field Code | Test Field Name |
| --- | --- |
| 005 | Elementary Education |
| 010 | Middle Level Humanities |
| 012 | Middle Level Mathematics |
| 013 | Middle Level Science |
| 021 | Science |
| 023 | Chemistry |
| 026 | Mathematics |
| 027 | History |
| 028 | Social Studies |
| 030 | Reading |
| 050 | Bilingual Education |
| 051 | English as a Second Language |