Phase 2 WEST-E Test Development Milestones (Fields in Test Development Groups 3 & 4)

Draft December 21, 2007

| Activity | Tentative Timeframe |  |
| --- | --- | --- |
| COMMITTEE ESTABLISHMENT |  |  |
|  | Group 3 | Group 4 |
| Secure from PESB the names of potential committee members and recruitment contacts | February - March 2008 | April - May 2008 |
| Draft/send recruitment mailing/nomination forms to recruitment contacts | April-June 2008 | June-September 2008 |
| Follow-up with recruitment contacts | April-June 2008 | June-September 2008 |
| PESB approve committees | April-June 2008 | June-September 2008 |
| PRELIMINARY TEST FRAMEWORK REVIEWS (by Mail, Phone & E-mail) |  |  |
|  | Group 3 | Group 4 |
| Preliminary Test Framework Reviews (OSPI staff & IHE reps) | March -May 2008 | May - July 2008 |
| TEST DEVELOPMENT CONFERENCES |  |  |
|  | Group 3 | Group 4 |
| Draft/send invitations to Test Development Conferences | June 2008 | September 2008 |
| Conduct Test Development Conferences (Fairness Review & Content Advisory Committees; OSPI staff as observers) | July 2008 | October 2008 |
| CONTENT VALIDATION SURVEY |  |  |
| Distribute surveys | January 2009 |  |
| Follow-up with survey recipients | January 2009-April 2009 |  |
| Complete survey data analysis/finalize Test Frameworks | May 2009 |  |
| PILOT TESTS |  |  |
| Draft/send site recruitment mailing | December 2008 |  |
| Conduct follow-up with site contacts | January-February 2009 |  |
| Conduct pilot test | March-April 2009 |  |
| Complete pilot test data analysis/finalize test items | May 2009 |  |
| Blueprint first test forms | June 2009 |  |
| STUDY GUIDES/PRACTICE TESTS |  |  |
| Distribute Study Guides/Practice Tests | June 2009 |  |
| MARKER ESTABLISHMENT/VALIDITY VERIFICATION/STANDARD SETTING |  |  |
| Conduct first test administration | September 2009 |  |
| Conduct Marker Establishment Conduct Validity Verification Conduct Standard Setting (Passing Score Panel) | October 2009 |  |
| PESB sets performance standards | November 2009 |  |
| Score reports sent/posted | December 2009 |  |

Test Development Group 3

Test Development Conference –July 2008 (Estimated)

| Test Field Code | Test Field Name |
| --- | --- |
| 037 | Agricultural Education |
| 038 | Business Education |
| 100-109 | Designated World Languages* (all except Latin) |
| 101 | Designated World Languages: Latin* |
| 001 | Early Childhood Education |
| 041 | Family and Consumer Sciences Education |
| 039 | Marketing Education |
| 070 | Special Education |
| 040 | Technical Education |
| 043 | Traffic Safety |

*Framework Review Only

Test Development Group 4

Test Development Conference –October 2008 (Estimated)

| Test Field Code | Test Field Name |
| --- | --- |
| 101 | Designated World Languages: Chinese** |
| 102 | Designated World Languages: French** |
| 103 | Designated World Languages: German** |
| 104 | Designated World Languages: Japanese** |
| 105 | Designated World Languages: Latin** |
| 106 | Designated World Languages: Norwegian** |
| 107 | Designated World Languages: Russian** |
| 108 | Designated World Languages: Spanish** |
| 109 | Designated World Languages: Swedish** |
| 071 | Early Childhood Special Education |
| 042 | Library Media |

**Item review only, includes CRIs