## Sheet1
2009 Hooding Ceremony and Graduation
Tracking Spreadsheet
| WHO | $ NEEDED |  |  | KEY | Task
WHAT | DOES IT | ? | Amount | Org | FACTS | # | TASKS | DATE | CONTACT PERSON | EMAIL | PHONE | COMMENTS POST EVENT
Date & Time | n/a |  |  |  | Fri 6/12/09; 10-12noon latest; doors at 9:30 | 1 | Set date and time | DONE
Location: Room Reservation | Randee |  |  |  | Recital Hall in Comm Bldg | 1 | as Longhouse n/a this year, after touring viable sites & consultation with students, faculty, staff, spoke with Shannon and John in Comm and reserved Recital Hall | 3/6/09; DONE | Shannon Stewart | stewarts@evergreen.edu | 867-5896
Meet to set/review tasks | Randee/JT |  |  |  |  | 1 | Review task list; determine/confirm who does what | 4/21/09 DONE
Room/Site Setup | Randee |  |  |  | Check-in: 4 tables in wide part of lobby downstairs | 1 | meet & go to Comm Bldg to plan site setup | 5/7/09 DONE
[6 empty] | 2 | meet to discuss/confirm site set up plan with Shannon | emailed 4/21/09
[7 empty] | Confirmed w/ Shannon that tables and chairs provided by Shannon/Comm Bldg -- no need for Facilities | 2009-06-02
Room: Sound | Randee |  |  |  |  | 1 | meet with Diana at Comm Bldg to plan sound setup | 5/7/09 DONE | Diana Schlesselman, Electronic Media | dianas@evergreen.edu | 867-6268
[6 empty] | 2 | email JT & Diana to meet | 2009-04-17
Food: Order & PO | JT | x |  | split bet MES & MPA: MPA 91111 |  | 1 | JT emailed to arrange
Asking Les & Don | Randee |  |  |  |  | 1 | emailed their assts; it's on their calendars | DONE
Main Speaker (MPA) | Cheryl |  |  |  | Russ Lehman | 1 | Cheryl will ask Nita; Nita can't do | 4/21/09 DONE
[6 empty] | 2 | Select/invite/confirm another speaker | DONE
[6 empty] | 3 | Cheryl asked Russ; he agreed | DONE
[6 empty] | 4 | Cheryl to email Russ/me to meet to discuss his speech
MPA Student Speaker | Randee |  |  |  | Corey Leneker | 1 | TBD by 5/11/09 | 5/5/09 DONE
[6 empty] | 2 | emailed Larry & Rene-Mark to ask to set aside 20 min in ATPS on 4/23 | 4/16/09 4/20/09
[6 empty] | 3 | email mpa-all to tell students to set up process to select speaker; name needed by 5/11/09 | 2009-04-22
[6 empty] | 4 | Students set up process and selected speaker in Capstone | 2009-05-02
[6 empty] | 5 | Randee given name of student | 2009-05-05
Program: Order & PO | Randee/Jan coord; Tricia creates | x |  | split bet MES & MPA:: MPA 25201 | 250; delivery goal is 6/4/09 | 1 | 250 programs for Hooding Ceremony |  |  |  |  | will need more (300?) in even years, when Tribal cohort graduates
[6 empty] | 2 | Emailed Jan 4/17; meet to discuss calendar & tasks | 2009-04-22
[6 empty] | 3 | Get printing estimate
[6 empty] | 4 | Given printer deadline, set deadlines for program input; email JT, Randee
[6 empty] | 5 | Edit program; give to Tricia by 5/14/09: prep lists (grad, faculty, staff names), other program info in Word
[6 empty] | 6 | Tricia preps program
[6 empty] | 7 | Jan sends final to Tumwater Printing
[6 empty] | 8 | Jan proofs and selects cover stock
[6 empty] | 9 | Printer sends final proof; Jan reviews/approves
[6 empty] | 10 | Delivery
Ceremony Flow | Randee |  |  |  | For program | 1 | emailed draft to Cheryl for review | 2009-04-20
[6 empty] | 2 | email to JT/Ted for review
[6 empty] | 3 | update program file in Word & email Tricia
Graduation info & reminders to MPA students | Randee |  |  |  | For program | 1 | email comprehensive grad email | 2009-04-29
List of MPA graduates | Randee |  |  |  | For program | 1 | Finalize list of graduates for program
[6 empty] | 2 | list of grads who've applied from Elaine
[6 empty] | 3 | Email grads to doublecheck their names
[6 empty] | 4 | Finalize, alphabetize and send to Tricia for program
Ushers | Randee |  |  |  | 4 needed | 1 | determine tasks & # needed
[6 empty] | 2 | email mpa-all to ask
[6 empty] | 3 | email ushers (all from MPA) Wed 6/10 to confirm: Leslie Wolff, April Denison, Lori Klatt (Jan needed for other tasks)
[6 empty] | 4 | email names to John and Shannon
Photos | JT |  |  |  | photog to take photo as grad is hooded + group shots | 1 | choose photographer: campus or Gradtrak
[6 empty] | 2 | given Carlos' irate call to R last year, R asked Lorri about whether it might cause a problem with the union to do what we did last yr: contract outside vendor GradTrak to take photos instead of Photo Services; she is asking Maryam and will get back to R | 2009-04-16
[6 empty] | 3 | R spoke with Lorri: Lorri spoke with Maryam who confirmed that there is no issue with choosing another vendor to do photos -- no contract bet. Evergreen and campus photog to do grad photos, and therefore union has no say | 2009-04-21
[6 empty] | 4 | R received email from Gradtrak to confirm that they are 09 Hooding Ceremony photog; R replied that we can't confirm yet as are talking with campus photog and refered to JT as this year's contact for photos | 2009-04-21
[6 empty] | 5 | JT emailed Campus Photog to describe type of photos we want and get samples; selected GradTrak
[6 empty] | 6 | JT asked Tricia & Randee for spreadsheets with MES and MPA grad contact info, emailed info to GradTrak
[6 empty] | 7 | In JT's absence Randee met with GradTrak staff b4 Ceremony re: photo setup & procedure | 2009-06-12
Music | JT |  |  |  | no $ therefore want recorded (CD) music b4 and after ceremony | 1 | determine music selections, how music/audio works in Recital Hall, who will coordinate that day |  |  |  |  | music worked well; began playing at 8:45
[6 empty] | 2 | Discuss with Diana at audio meeting
[6 empty] | 3 | Tricia met with Mary Ann Steele (who has lots of music CDs) and selected classical guitar CD; Jan offered music from home if needed
[6 empty] | 4 | In JT's absence Randee brought music to event and discussed setup w/sound staff
Decorations/Flowers | JT | x |  |  | Flowers only -- 2 arrangemnts: 1 lg (in front of podium) & 1 sm (vase upstairs) = $200 approx | 1 | Determine minimum decorations to make it look nice and how we'll get them ($ and/or borrow) | DONE |  |  |  | flowers beautiful, on time; use this vendor again
[6 empty] | 2 | In JT's absence Randee got estimates, spoke with Lorri to confirm that we could pay for flowers using state funds, Ted confirmed MES would split cost, ordered from Newberry Bay ($182 for 2 arrangements, Jan did PO, Randee spoke with Shannon re: placement of flowers)
Gift | Randee/JT | x |  | split bet. MPA Initiative (25220) & MES | no gift | 1 | MPA: will be discussed at 4/27 fac/staff meeting | 4/27/09 DONE
Regalia for students to borrow | Randee/JT |  |  |  | MPA: 1 hood that students can share | 1 | MPA: will be discussed at 4/27 fac/staff meeting | 4/27/09 DONE
[6 empty] | 2 | 1 student ended up using
Signs | Randee |  |  |  |  | 1 | Spoke with Shannon re: signs provided by Comm bldg
[6 empty] | 2 | At walkthrough determined need for/location of signs
[6 empty] | 3 | Bought black poster paper & made signs for 2 sandwich bds, walls and table
[6 empty] | 4 | Before ceremony posted signs; after ceremony removed
Last details meeting | Randee/JT | [5 empty] | Final meeting during week of graduation | did not happen

## Sheet2
Supplies to take
AV Cart from Lab 1 1st floor
Tape
Signs
Blank paper (to improv signs)
Pens
Marking pens
Programs
Hood
Check in cards
MPA tablecloth
Music CD
Ziplock bags
Post its
Staff
Randee | 7:45
Jan | 8 | Catering check in, back up, possibly move to ushering mid-ceremony
Leslie | 8:45 | usher
April | 8:45 | usher
Lori | 8:45 | usher til 11am
Maggie | 8:45 | check in table, move to ushering mid ceremony
Jane Fisher (Alum Adv Bd rep) | ? | greet OR MES check in table

## Sheet3
Tasks by Time
Th 6/11 | 1 day before
Get cart; load to bring stuff to Comm
| Comm with Jan and Maggie | do earlier next year
| Usher confirming email | do earlier next year
Hood borrower confirming email
| Meet with Shannon, get key to side room, load stuff in | do earlier next year
| Front row reserve -- photog seat | do earlier next year
| Lighting confirm | do earlier next year
| Podium & flower pedestals | do earlier next year
| Signs: count # & type needed, make | do earlier next year
Fr 6/12 | THE Day | Police Services x6832 (if doors locked, etc) | Shannon x5896 Com303B
When | What | Who | How (supplies/instructions)
7:45 | Randee get there; get cart from Green Room
8 | Jan get there
8 | Ted get there (for MES: JT out)
8 | Sound get there, open building |  | Diana x6268
8 | Catering get there | Jan (in JT abs) | Kitchen x5275
by 8:10 | Check in with House Mgr
| 5 Reserved seats: CK, Ted, Russ, photog 1&2 | Randee/House mgr | get laminated signs to hold seats
8:10 | Signs -- construct, put up/out | Randee/Jan/House mgr | need sandwich bds from ticket office
| Music confirm -- CD to sound people | Randee (in JT abs) | play music 9:15-ceremony beginning at 10; then when ceremony ends
| Photog -- sit in front row | Randee (in JT abs)
8:45 | Ushers get there, report to House mgr for training | Leslie, Lori, April | tell them where other Hooding Ceremonies are -- MIT/MEd in CRC, etc
8:45 | Flowers -- pick up at curb; arrange | Randee or Jan | take cart; Lena cell 402-5571
8:45 | Check in table set up/running | Maggie
9:15 | Start music | Randee (in JT abs)/sound crew
9:50 | Hood to Michael or Rick | Maggie
9:55 | Les and Don there? | Randee | Les/Susan x6100; Don/Linda x6400
10:00 | Stop music when Cheryl speaks | Randee cue
10:50 | or as Russ is finishing -- ushers go out to direct grads to location
11 | Check -- is any food left? If so, put out ziplocks, let CK know for her speech
Hood back from Rick or Darleen
Take cart & stuff back to Lab 1
Keys back to Shannon