## Tasks
2010 Hooding Ceremony and Graduation
Tracking Spreadsheet
| WHO | $ NEEDED |  |  | KEY | Task
WHAT | DOES IT | ? | Amount | Org | FACTS | # | TASKS | DATE | CONTACT PERSON | EMAIL | PHONE | COMMENTS POST EVENT
Date & Time | n/a |  |  |  | Fri 6/11/10; 10-12noon latest followed by MPA Alum Assn reception; doors at 9:30 | 1 | Set date and time | DONE
Location: Room Reservation | Randee |  |  |  | Longhouse | 1 |  | DONE
Meet to set/review tasks | Randee/Gail |  |  |  |  | 1 | Review task list; determine/confirm who does what | 2010-05-05
Room/Site Setup | Gail | x |  |  | Check-in: 4 tables in wide part of lobby downstairs | 1 | contact Facilities re: doing work order
[6 empty] | 2 | meet & go to Longhouse to plan site setup
[6 empty] | 3 | Jan/Tricia count chairs
[6 empty] | 4 | Site plan to Facilities
Room: Sound | Gail | x |  |  |  | 1 | contact/meet with Diana to plan sound setup |  | Diana Schlesselman, Electronic Media | dianas@evergreen.edu | 867-6268
Food: Order & PO | Maggie | x |  | split bet MES 25101 (1/3) & MPA 91111 (2/3s) |  | 1
Asking Les & Ken | Randee |  |  |  |  | 1 | emailed their assts; it's on their calendars | DONE
Main Speaker | MES |  |  |  | Gerardo Chin-Leo | 1 | Added to program info | 2010-05-05
MPA Student Speakers | Randee/Maggie |  |  |  | Grady Smith MPA gen; Dylan Dressler MPA Tri | 1 | Email cohorts re: info about speaking and deadline. | done
[6 empty] | 2 | TBD by each cohort by 5/3/10 | 5/3/10 DONE
3
4
5
Program: Order & PO | Randee/Jan coord; Tricia creates | x |  | split bet MES 25101 (1/3) & MPA 25220 (2/3s) | 450; files to them M 5/24/10; they deliver Th 6/3/10 | 1 | Jan got printing estimate | 2010-04-08 |  |  |  | will need more (300?) in even years, when Tribal cohort graduates
[6 empty] | 4 | Given printer deadline, set deadlines for program input; email JT, Randee
[6 empty] | 5 | Edit program; give to Tricia by 5/14/09: prep lists (grad, faculty, staff names), other program info in Word
[6 empty] | 6 | Tricia preps program
[6 empty] | 7 | Jan sends final to Tumwater Printing
[6 empty] | 8 | Jan proofs and selects cover stock
[6 empty] | 9 | Printer sends final proof; Jan reviews/approves
[6 empty] | 10 | Delivery | 2010-06-03
Ceremony Flow | Randee |  |  |  | For program | 1 | emailed draft to Cheryl and Martha for review | 2010-05-03
[6 empty] | 2 | emailed reminder to all to get stuff in | 2010-05-18
[6 empty] | 2 | update program file in Word & email Tricia | 2010-05-18
3
Graduation info & reminders to MPA students | Randee |  |  |  | For program | 1 | email comprehensive grad email
List of MPA graduates | Randee |  |  |  | For program | 1 | Finalize list of graduates for program
[6 empty] | 2 | list of grads who've applied from Elaine
[6 empty] | 3 | Email grads to doublecheck their names
[6 empty] | 4 | Finalize, alphabetize and send to Tricia for program | 2010-05-18
Ushers | Randee |  |  |  | 4 needed for each program | 1 | determine tasks & # needed | done
| Gail |  |  |  |  | 2 | email mpa-all to ask | done
[6 empty] | 3 | MPA ushers: Laura Coghlan, Lori Klatt (til 11), Amadou Ba, Alicia LeDuc, Tribal student
[6 empty] | 4 | email ushers Tues 6/8 to confirm
5
Photos | Maggie |  |  |  | photog to take photo as grad is hooded + group shots | 1 | email Gradtrak to confirm | 2010-05-13
[6 empty] | 2 | get spreadsheets with MES and MPA and MPA tribal grad contact info, email info to GradTrak
[6 empty] | 3 | meet with GradTrak staff b4 Ceremony re: photo setup & procedure
4
5
6
[6 empty] | 7 |  | 2009-06-12
Music | Gail/ Tricia |  |  |  | no $ therefore want recorded (CD) music b4 and after ceremony | 1 | determine music selections, how music/audio works in Longhouse, who will coordinate that day |  |  |  |  | music worked well; began playing at 8:45
[6 empty] | 2 | Tricia got CD
[6 empty] | 3 | Bring music to event
Decorations/Flowers | Randee/Jan | x |  |  | Flowers only -- 2 arrangemnts: 1 lg (in front of podium) & 1 sm (vase upstairs) = $200 approx | 1 | Determine minimum decorations to make it look nice and how we'll get them ($ and/or borrow) | DONE | 2011- Artistry in Flowers | Gail; cell 360-280-8563 |  | 2010: flowers beautiful, on time; use this vendor again
[6 empty] | 2 | Randee got estimates, spoke with Lorri to confirm that we could pay for flowers using state funds, ordered from Newberry Bay ($182 for 2 arrangements, Jan did PO,
Gift | MPA | x |  | split bet. MPA Initiative (25220) & MES | no gift | 1 | MPA: will be discussed at April fac/staff meeting | done
[6 empty] | 2 | MPA: decision at 5/10 fac/staff -- no gift | 2010-05-10
Regalia for students to borrow | Randee |  |  |  | MPA: 2 hoods that students can share | 1 | MPA: will be discussed at 4/27 fac/staff meeting | 4/27/09 DONE
[6 empty] | 2 | 1 student ended up using
Signs | Randee |  |  |  | 2 signs, 1 on way to Longhouse, 1 at bus loop | 1 | Spoke with Shannon and John to see if Comm bldg signs available; Nope :-(
[6 empty] | 2 | Referred to Ahoi and Bob Worley -- Bob does all graduation signs and MPA/MES never been part of this
[6 empty] | 3 | Spoke with Bob: they will make and put up 3 signs
[6 empty] | 4 | Sent sign instructions to Bob; can only do 2 signs
Last details meeting | All | [5 empty] | Final meeting during week of graduation | did not happen

## Supplies
Supplies to take: 2011
AV Cart from Lab 1 1st floor | J
Tape | J
Signs | J
Blank paper (to improv signs) | J
2 Marking pens | J
Programs | J
Check in table folder | J
Pens for check in table | J
check-in list for volunteers | J
Post its | J
Commencement yellow check in cards | J
MPA tablecloth | J
Music CDs | R
room set up diagram | R
contact info for key people | R
MPA Hoods | R
Randee's graduation folder | R
Copy of this spreadsheet | R
Copy of script | R
decorations | R
Staff
Randee | 7am | Overall set up/coord
Jan | 7am | catering, signage, flowers, check in
Jerry | 8am | photos, check in if needed
Emily Sladek | 8:45am | student vol -- check in
Estrella Shepherd | 8:45am | student vol -- usher
Chris Novelli | 8:45am | student vol -- usher
Alejandro Rugarcia | 8:45am | student vol -- outside 2nd floor Lib to direct people
Hood Borrowers
Abby Kelso
Abi McLane
Gina Nakamura
Walter Neal

## Tasks by Time
Tasks by Time | 2011
W 6/8 | 2 days before
| Check room: stage set up, chair set up | R
| See when organ/keyboard set up | R
| See when musicians can do sound check | R
Th 6/9 | 1 day before
Finish script
| Get cart; load to bring stuff | Jan/Randee
3:00 | Visit Lib4300 to check on sound | Randee
Usher confirming email
Hood borrower confirming email
Decorations
1:00 | Sound set up/check? | Diana/Mike/Mitch
| Signs on tables (food, cover w/linen) | Randee
Fr 6/10 | THE Day | Police Services x6832 (if doors locked, etc)
When | What | Who | How (supplies/instructions)
7:00 | Randee get in go to Lib 4300 | Randee
7:00 | Jan get in, get cart from Lab 1 | Jan
7:15 | Double check set up, put up any decorations, set up check in table | Randee | Facilities: Gaylon x6347; main x6120; Kat x 6317
7:15 | Put up signs: 2nd floor Lib, bathrooms; put up signs to reserve seats for front row, cohort, faculty | Jan
7:30 | Sound get there, begin sound check | Randee | Diana x6268; Giles and Mike working event
8:00 | Jerry get there | Jerry
8 | Photog get there -- sit in front row, get oriented | Jerry
8 | Music confirm -- CD to sound people | Randee | play music 9 -- ceremony beginning at 10; then when ceremony ends
? | Singers/musicians do sound check | Randee/sound/musicians
8:30 | Catering arrive to set up | Jan | Kitchen x5275; Barb x5017
8:30 | Flowers -- pick up at curb; arrange | Jan | Artistry in Flowers -- Gail; cell 360-280-8563
8:45 | Check in table set up/running | Emily
8:45 | Ushers get there | Alejandro, Estrella, Emily, Chris | tell them where other Hooding Ceremonies are -- MIT/MEd in Longhouse at 10am, MES in Comm bldg Recital Hall at 10:30
9:00 | People typically arrive; start music | Randee cue sound
9:30 | Doors open
9:30 | Hoods to people (Abby, Abi, Gina, Walter) | Randee
9:45 | Speakers there: Bryce, Cheryl?
10:00 | Ceremony to begin: Stop music when Lee to speak | Randee cue
10:05 | Ken there? | Randee cue Lee | Les/Susan x6100; Ken/Linda x6400
10:15 | Les there? | Randee cue Lee | Les/Susan x6100; Ken/Linda x6400
Hood back from last people
M 6/14 | Take cart & stuff back to Lab 1
by T 6/15 | Take box and fabric back to Comm if nec

## Contact info
Important Phone Numbers - 2011
Who | # | Reasons
Police | x6832 | doors locked, problems
Facilities | x6347 Gaylon; | bathroom, set up issues, mess to clean up
x6120 main
x6317 Kat
Catering | x5017 Barbara | refills, messy tables, late
x5275 Kitchen
Sound | x6268 Diana | problems
Flowers | Gail cell 360-280-8563
Jan cell | 206-235-2460
Randee cell | 360-359-5034
Randee office | 360-867-6554