## Tasks
2013 Hooding Ceremony and Graduation
Tracking Spreadsheet
| WHO | $ NEEDED |  |  | KEY | Task
WHAT | DOES IT | ? | Amount | Org | FACTS | # | TASKS | DATE | CONTACT PERSON | EMAIL | PHONE | COMMENTS POST EVENT
Date & Time | n/a |  |  |  | Fri 6/14/13; 10-12noon latest; doors at 9:30 | 1 | Set date and time | DONE
Location: Room Reservation | Randee |  |  |  | CRC | 1 |  | DONE
Meet to set/review tasks | Randee |  |  |  |  | 1 | Review task list; determine/confirm who does what | 2010-05-05
Room/Site Setup | Randee | x |  |  | Check-in: 4 tables in wide part of lobby downstairs | 1 | Meet with Loren in MIT re: past history | 2013-03-01
[6 empty] | 2 | contact Facilities re: doing work order
[6 empty] | 3 | Met with Loren again, consulted with Andrew as we want to enter through back bay through CRC lobby (vs. in back)
[6 empty] | 4 | Site plan to Facilities | 2013-06-11
Room: Sound | Randee | x |  |  |  | 1 | contact Ben Hargett to plan sound setup |  | Diana Schlesselman, Electronic Media | dianas@evergreen.edu | 867-6268
Food: Order & PO | Jan | x |  | MPA 91111 |  | 1 | Meet with Gail to see good finger food, cost, # | 2013-04-29
2
Asking Les & Michael | Randee |  |  |  |  | 1 | emailed their assts; it's on their calendars | DONE
Main Speaker | Lee |  |  |  | WA State Rep Sam Hunt | 1 | Randee added to program info | 2013-04-01
MPA Faculty Speaker | Lee |  |  |  | Doreen Swetkis |  | Randee added to program info | 2013-04-01
MPA Student Speaker/Presentation | Randee/Capston fac/cohort |  |  |  | DJ Crisostomo, speaker only, no media used | 1 | Email Capstone fac re: info about speaking and deadline. | done
[6 empty] | 2 | emailed students that they need to choose speaker and to email Jan name by 5/20 | 2013-04-30
[6 empty] | 3 | Jan was emailed DJ's name | 2013-05-28
[6 empty] | 4 | Randee emailed DJ to see if he was using any media, need to bring laptop if so | 2013-05-31
MPA Student Speaker at Commencement
Program: Order & PO | Jan coord & creates | x |  | MPA 25220 | 400 programs; file to them 6/4; they deliver M 6/10/13 | 1 | Jan printing estimate: 350/375/400; date needed | emailed 4/29/13 |  |  |  | will need more in even years, when Tribal cohort graduates
[6 empty] | 2 | Given printer deadline, set deadlines for program input; email Randee
[6 empty] | 3 | Jan preps program
[6 empty] | 4 | Jan sends final to Tumwater Printing
[6 empty] | 5 | Jan proofs and selects cover stock
[6 empty] | 6 | Printer sends final proof; Jan reviews/approves
[6 empty] | 7 | Delivery | 2013-06-07
Ceremony Flow | Randee |  |  |  | For program | 1 | prep draft of program
emailed draft to MPA Director
emailed speakers with timing guidelines
[6 empty] | 2 | emailed reminder to Jan to input rest of stuff, with deadlines
[6 empty] | 2 | received/culled student names, provided to Jan
3
Graduation info & reminders to MPA students | Randee |  |  |  | For program | 1 | email comprehensive grad email
List of MPA graduates | Randee |  |  |  | For program | 1 | Finalize list of graduates for program
[6 empty] | 2 | list of grads who've applied from Elaine
[6 empty] | 3 | Email grads to doublecheck their names
[6 empty] | 4 | Finalize, alphabetize and send to Tricia for program | 2010-05-18
Ushers | Randee |  |  |  | 4 needed for each program | 1 | determine tasks & # needed | done
[6 empty] | 2 | email mpa-all to ask | done
[6 empty] | 3 | MPA ushers: Laura Coghlan, Lori Klatt (til 11), Amadou Ba, Alicia LeDuc, Tribal student
[6 empty] | 4 | email ushers Tues 6/8 to confirm
5
Photos | Randee |  |  |  | photog to take photo as grad is hooded + group shots | 1 | contacted campus photog
[6 empty] | 2 | confirmed name -- Karissa Carlson, starting 8:30
[6 empty] | 3 | Emailed GradTrack that we are not using them | 2013-06-12
Music | Randee |  |  |  | no $ therefore want recorded (CD) music b4 and after ceremony | 1 | determine music selections, how music/audio works in Longhouse, who will coordinate that day |  |  |  |  | music worked well; began playing at 8:45
[6 empty] | 2 | Tricia got CD
[6 empty] | 3 | Bring music to event
Decorations/Flowers | Jan | x |  |  | Flowers only -- 2 arrangemnts: 1 lg (in front of podium) & 1 sm (vase upstairs) = $200 approx | 1 | Determine minimum decorations to make it look nice and how we'll get them ($ and/or borrow) | DONE | 2011- Artistry in Flowers | Gail; cell 360-280-8563 |  | 2010: flowers beautiful, on time; use this vendor again
[6 empty] | 2 | Randee got estimates, spoke with Lorri to confirm that we could pay for flowers using state funds, ordered from Newberry Bay ($182 for 2 arrangements, Jan did PO,
Gift | MPA | x |  | split bet. MPA Initiative (25220) & MES | no gift | 1 | MPA: will be discussed at April fac/staff meeting | done
[6 empty] | 2 | MPA: decision at 5/10 fac/staff -- no gift | 2010-05-10
Regalia for students to borrow | Randee |  |  |  | MPA: several sets + hoods available | 1 | Jan emailed & made list
[6 empty] | 2 | Randee brought to Capstone
[6 empty] | 3 | Bring extra hoods to ceremony
Signs | Jan |  |  |  |  | 1 | List to make sent to Jan via email
2
Last details meeting | Jan/Randee | [5 empty] | Final meeting Thurs | did not happen

## Supplies
Supplies to take: 2013
AV Cart from Lab 1 1st floor
Tape
Signs
Blank paper (to improv signs)
2 Marking pens
Programs
Check in table folder | R
--check-in list for volunteers
--Copy of contact info of impt people
--Copy of supply list
Pens for check in table
Post its
Commencement yellow check in cards
MPA tablecloth
1st aid kit
Box of Kleenex
Extra hoods
Jan's knife
Extra tea bags
Gifts
Signs
Name tags
Music CDs | R
room set up diagram
Randee's graduation folder | R
--Copy of contact info of impt people
--Copy of script
--Copy of supply list
MPA brochures
scissors
Staff
Randee | 7am | Overall set up/coord, student vol, check in, photos, sound
Jan | 7am | cart from Lab 1, catering, signage, flowers, check in
Puanani |  | help where needed
Abby Kelso, alum | 8:45am | student vol -- check in
Debra Allen-Ba | 8:45am | student vol -- usher
Amanda Rains, student | 8:45am | student vol -- usher
Gloria Martin, student | 8:45am | student vol -- usher
Andrew Beattie, student | 8:45am | student vol -- usher
Regalia Borrowers -- need to get back from them
Alisa Solberg | hood
Caitlin White | hood
David Faro | cap/gown
Faith Hawks | cap/gown
Katja Bishop | cap/gown/hood
Marty Heaverlo | cap/gown/hood
Shirley Serven | cap/gown/hood
Sarah Rocker | hood

## Tasks by Time
Tasks by Time | 2013
Th 6/13 | 1 day before
| Check room: stage set up, chair set up | Randee
| Finish script | Randee
| Get cart; load to bring stuff | Jan
| Complete signs, see where they should be placed | Jan
| Usher confirming email | Randee
Fr 6/14 | THE Day | Police Services x6832 (if doors locked, etc)
When | What | Who | How (supplies/instructions)
7:00 | Randee get in go to Lib 4300 | Randee
7:00 | Jan get in, get cart from Lab 1 | Jan
7:15 | Double check set up, put up any decorations, set up check in table | Randee | Facilities: Kat x6347; main x6120; Tammy x 6317
7:30 | Put up signs: including to reserve seats for front rows for cohort, faculty | Jan
7:30 | Sound get there, begin sound check | Randee | Ben cell 360-463-3059; Leon is lead + 1 other person working event
8 | Music confirm -- CD to sound people | Randee | play music 9 -- ceremony beginning at 10; then when ceremony ends
8:30 | Photog get there -- sit in front row, get oriented; see how to take photo of cohort | Randee
8:30 | Catering arrive to set up | Jan | Kitchen x5275; Barb x5017
8:30 | Flowers -- pick up at curb; arrange | Jan | Artistry in Flowers -- Gail; cell 360-280-8563
8:45 | Check in table set up/running | Emily
8:45 | Ushers get there | Randee | tell them where other Hooding Ceremonies are
9:00 | People typically arrive; start music | Randee cue sound
9:30 | Doors open
9:45 | Speakers there: Lee, DJ, Doreen, Sam Hunt
9:45 | Get proc from CK -- stash with check in table stuff
10:00 | Ceremony to begin: Stop music when Lee to speak | Randee cue
10:05 | Michael there? | Randee cue Lee | Les/Susan x6100; Michael/Marcia x6400
10:15 | Les there? | Randee cue Lee | Les/Susan x6100; Michael/Marcia x6400
Hood back from last people
M 6/14 | Take cart & stuff back to Lab 1
by T 6/15 | Take box and fabric back to Comm if nec

## Contact info
Important Phone Numbers - 2013
Who | # | Reasons
Police | x6832 | doors locked, problems
Facilities | x6347 Kat | bathroom, set up issues, mess to clean up
x6120 main
x6317 Tammy
Catering | x5017 Barbara | refills, messy tables, late
x6281 Samantha-catering manager
x5275 Kitchen
Sound | x6268 Ben's office; for day of, here's his cell: 360-463-3059 | problems
Flowers | artistry in flowers- 357-3557
Jan cell | 206-235-2460
Randee cell | 360-359-5034
Randee office | 360-867-6554