## Tasks
2015 Hooding Ceremony and Graduation
Tracking Spreadsheet
| WHO | $ NEEDED |  |  | KEY | Task
WHAT | DOES IT | ? | Amount | Org | FACTS | # | TASKS | DATE | CONTACT PERSON | EMAIL | PHONE | COMMENTS POST EVENT
Date & Time | n/a |  |  |  | Fri 6/12/15; 10-12noon; doors at 9:15 | 1 | Set date and time | DONE
Location: Room Reservation | Randee |  |  |  | CRC | 1 | Reserve room for F 6/12 and Th 6/11 for setup | DONE
[6 empty] | 2 | After Michele confirms email Space Sched and Longhouse
Meet to set/review tasks | MPA staff |  |  |  |  | 1 | Review task list; determine/confirm who does what | DONE
Room/Site Setup | Laura | x |  |  | Check-in: 4 tables in wide part of lobby downstairs | 1 | contact Facilities re: doing work order |  |  | Laura and Randee create diagram for Kat on 5/26 | determine stage size | Make work order and meet with Kat
[6 empty] | 2 | meet & go to CRC to plan site setup
[6 empty] | 3 | Site plan to Facilities
Room: Sound | Laura | x |  |  |  | 1 | contact/meet with Benjamin H to plan sound setup |  | Electronic Media | Ben is waiting for final sound plan
Food: Order & PO | Jan | x |  |  |  | 1 | See last 2 years orders: last year for food, 2013 for quantities |  |  | Jan Laura and Randee will look at set up options 5/26
Asking Les & Michael | Randee |  |  |  |  | 1 | emailed their assts; it's on their calendars | DONE
Main Speaker | Laura |  |  |  |  | 1 | ask Craighill about ethics of polical speaker |  | Cheryl will invite | Jessica Bateman | DONE
Student Speaker | Randee |  |  |  |  | 1 | R email faculty re: info about speaking and deadline | DONE |  | Bary Hanson | Laura e-mailed for media requests
[6 empty] | 2 | Names to be sent to Jan by 5/12/14
[6 empty] | 3 | Students to send intro blurbs to Cheryl by 6/2/14
Program: Order & PO | Laura and Jan | x |  |  | 350; files to them may 27; they deliver M 6/8/14 | 1 | Jan requested printing estimate |  |  |  |  | will need more (300?) in even years, when Tribal cohort graduates
| Laura |  |  |  |  | 4 | Given printer deadline, set deadlines for program input;
[6 empty] | 5 | Edit program; give to Jan by : prep lists (grad, faculty, staff names), other program info in Word | 2014-04-28 | 1st draft |  | Jan to edit faculty | Lori needs to send names for us to send out the student check e-mail 4/18
[6 empty] | 6 | Jan preps program
[6 empty] | 7 | Jan sends final to Tumwater Printing
[6 empty] | 8 | Jan proofs and selects cover stock
[6 empty] | 9 | Printer sends final proof; Jan reviews/approves
[6 empty] | 10 | Delivery
Ceremony Flow | Laura |  |  |  | For program | 1 | email draft to Cheryl for review
[6 empty] | 2 | emailed reminder to all to get stuff in
[6 empty] | 2 | update program file in Word & email Tricia | ????
Graduation info & reminders to MPA students | Randee |  |  |  | For program | 1 | email comprehensive grad email |  |  |  |  | Laura send parking, photo and cell phone e-mail out on Thusday 4/21
Laura
# of participants | Laura |  |  |  |  | 1 | R &P ask cohorts who will be attending and how many guests | R: in Cap via spreadsheet on 4/10/14;
Laura
List of MPA graduates | Laura |  |  |  | For program | 1 | Finalize list of graduates for program- talk with Randee, Lori K. and Elaine | R emailed Lori, 5/14 emailed again
[6 empty] | 2 | list of grads who've applied from Elaine
| Laura |  |  |  |  | 3 | Email grads to doublecheck their names
[6 empty] | 4 | Finalize, alphabetize for program
Volunteers | Laura |  |  |  | 4 needed for each program | 1 | determine tasks & # needed | done |  |  |  | porsam25@evergreen.edu | Sam
[6 empty] | 2 | email mpa-all to ask | done |  |  |  | stamarol@evergreen.edu | Gwen
[6 empty] | 3 | email ushers Tues 6/9 to confirm
Photos | Laura |  |  |  | campus photog | 1 | pictures before ceremony | DONE
[6 empty] | 2 | Meet 1-2 weeks b4 graduation |  |  |  |  | Work order finished
Music | Puanani |  |  |  | no $ therefore want recorded (CD) music b4 and after ceremony | 1 | determine music selections, how music/audio works in CRC, who will coordinate that day |  |  |  |  | music worked well; began playing at 8:45
[6 empty] | 2 | Tricia got CD
[6 empty] | 3 | Bring music to event
Decorations/Flowers | Puanani/Jan | x |  |  |  | 1 | Determine minimum decorations to make it look nice and how we'll get them ($ and/or borrow) | DONE | 2011- Artistry in Flowers | Gail; cell 360-280-8563 |  | 2010: flowers beautiful, on time; use this vendor again
[6 empty] | 2 | Randee got estimates, spoke with Lorri to confirm that we could pay for flowers using state funds, ordered from Newberry Bay ($182 for 2 arrangements, Jan did PO,
Gift | MPA | x |  | MPA Initiative (25220) | no gift |  |  | done
Regalia for students to borrow | Jan |  |  |  | MPA: several hoods but only 2 gowns
Signs | Laura |  |  |  | 2 signs, 1 on way to CRC, 1 at bus loop | 1 | Spoke with Shannon and John to see if Comm bldg signs available; Nope :-( |  |  |  |  | Laura asked Graduation offices for 4 sanwich board signs for entrance at c/ red square/ lot b and commons area c
[6 empty] | 2 | Referred to Ahoi and Bob Worley -- Bob does all graduation signs and MPA/MES never been part of this
[6 empty] | 3 | Spoke with Bob: they will make and put up 3 signs
[6 empty] | 4 | Sent sign instructions to Bob; can only do 2 signs
Last details meeting | All | [5 empty] | Final meeting during week of graduation | did not happen

## Supplies
Supplies to take: 2012
AV Cart from Lab 1 1st floor
Tape
Signs
Blank paper (to improv signs)
2 Marking pens
Programs
Check in table folder | R
--check-in list for volunteers
--Copy of contact info of impt people
--Copy of supply list
Pens for check in table
Post its
Commencement yellow check in cards | R
MPA tablecloth
1st aid kit
Box of Kleenex
Regalia for each borrower | R
Hoods | R
Laptops | R
Jan's knife
Extra tea bags
Gifts
"Reserved" signs
"Gluten-free" signs
Name tags
Music CDs | R
room set up diagram
Randee's graduation folder | R
--Copy of contact info of impt people
--Copy of script
--Copy of supply list
MPA brochures
scissors
Staff
Erin | 7am | Overall set up/coord, photos, sound
Randee | 7am | Key, overall set up/coord backup, student vol, check in
Jan | 7am | cart from Lab 1, catering, signage, flowers, check in
Abby Kelso | 8:45am | student vol -- check in
Debra Allen-Ba | 8:45am | student vol -- usher
Abdullatif Qaasim | 8:45am | student vol -- usher
Eric Lohnes | 8:45am | student vol -- usher
Heather Genia | 8:45am | student vol -- photos, chair rover/usher
Regalia Borrowers -- need to get back from them
Ada Daniels | full regalia -- might have previously picked up | already picked up
Justin Montermini | full regalia | needs to pick up
Kendra Aguilar | just gown | needs to pick up
Fernando Luna | full regalia | already picked up

## Tasks by Time
Tasks by Time | 2015
W | 2 days before |  |  | Comments
| Finish script | Randee
| Kat & crew set up: meet in CRC to check stage, chair (# and config), tables, check aisles & sightlines, etc; ideal to finalize Facilities work | R/J/P | Bring scissors and tape measure | Asked them not to tie the chairs in the middle section so we can move around
| Practice name pronunciation, copy to Dir | Randee
Th | 1 day before
| Finalize set up: check aisles & sightlines, put signs w/grad names, reserved guest seating, wheelchair/handicapped seating, etc | R/J/P/L | Bring scissors and tape measure | Ended up moving around seating, changing middle section to grads and location of wheelchairs
| Get cart; load to bring stuff | Jan
Usher confirming email
Hood borrower confirming email
| Table/"hole in wall" decorations | Jan
Sound set up/check?
| Signs for tables (food) | Jan
Decorations
| Met w/photographer | Randee | Ryan, works in Photo Services
| Buy flowers at Farmers Mkt for speakers & table | Jan & Puanani | 3 small bouquets + 1 large table bouquet = $48 (will be reimbursed by MPASU)
Fr 6/12 | THE Day | Police Services x6832 (if doors locked, etc)
When | What | Who | How (supplies/instructions)
7:00 | Randee arrives at CRC | Randee
7:15 | Jan & Puanani meet at Lab 1, get cart from Lab 1 | Jan & Puanani
7:30 | Double check set up | J/P/R | Facilities: Kat (x6317; main x6120)
7:15 | Sound get there, begin sound check | Randee | Ben x6268; Ben, Ben & Jon working event
8:00 | Laura arrives at CRC | Laura
8 | Music confirm -- CD to sound people | Puanani -- tell them to play CD by 9am unless people get there sooner | play music 9 -- ceremony beginning at 10; then when ceremony ends
8:30 | Photog get there -- sit in front row, get oriented
8:30 | Catering arrive to set up | Jan | Kitchen x5275; Barb x5017
8:45 | Check in table set up/running | Randee w/Jan
9:00 | Ushers get there: Laura orient | Laura, w/ Maureen & Gwen | tell them where other Hooding Ceremonies are -- MIT in Longhouse at 10am, MES in Comm bldg Recital Hall at 10:30
9:00 | People typically arrive; start music | Sound
9:15 | Doors open
9:30 | Hoods to people | Jan
9:35 | At mic, announce grads gather at front for group photo in 5 min | Randee
9:40 | Grads gather for photos/photos taken | Randee/Ryan
9:45 | Speakers there: Cheryl, Jessica, Amy, Bary? | Randee
9:58 | After photos taken, remove chairs | R/P/L
10:00 | Ceremony to begin: Stop music when Cheryl to speak | Randee cue
10:05 | Les there? (Les is first) | Randee cue Cheryl | Les/Susan x6100; MZ/Marcia x6400
10:15 | MZ there? (MZ is second) | Randee cue Cheryl | Les/Susan x6100; MZ/Marcia x6400
10:20 | Set up tables in front for Catering | R/P/L/J
10:30 | Catering arrive to set up | Jan | ?Kitchen x5275; Barb x5017?
Hood back from last people
Take cart & stuff back to Lab 1
Thank you notes to volunteers and staff
Debrief

## Contact info
Important Phone Numbers - 2015
Who | # | Reasons
Police | x6832 | doors locked, problems
Facilities | x6120 main | bathroom, set up issues, mess to clean up
x6317 Kat
CRC | x6528 Andrew | problems
Catering | x5275 Kitchen | refills, messy tables, late
x5017 Barbara
Sound | x6268 Ben | problems
Jan cell | 206-235-2460
Randee cell | 360-359-5034
Randee office | 360-867-6554
Cheryl cell | 360-485-7763