## Graduation TRACKING
| 2016 Hooding Ceremony TRACKING |  |  | Doreen's cell | 216 926 5085
|  |  |  | Jan's cell | 206 235 2460
|  |  |  | Puanani's cell | 360 742 2679
√ | 2016-04-05 | Work order-SUBMITTED #10484
|  | Staging & seating at Longhouse |  |  |  | Volunteers: | MUST Confirm
|  | Kat contacted 4/6 |  |  |  | Raquel Salinas | X6462 | Raquel will send a student
√ | 2016-04-06 | Request for photographer-SUBMITTED
|  | *Shauna will respond after inauguration 04/22 |  |  |  | Welcome | Tina Kuckkahn
[6 empty] | Opening Prayer: | Julie Johnson
√ | 2016-04-06 | Visual/audio contact made w/Ben Hargett |  |  |  |  | 360 640 0222/juliejj2012@gmail.com
| 2016-04-07 | *Confirmed w/Ben-Audio in cedar rm. Incl.
√ | 2016-04-06 | Jan's working w/catering |  |  |  | Longhouse capacity |  | 440
|  | Flavored water, veggie platters, tea sandwiches: tuna, chicken & cucumber w/cream chz |  |  |  | 90 | Approx. graduates 60-PNAPP & 27-TG
[6 empty] | 4 | Guest/graduate
| 2016-04-06 | Printing of programs-Jan working w/Tumwater printers-Stacia |  |  |  | 360 | # if ALL grads will be particpating in the hooding ceremony (never the case)
| 2016-04-11 | *Cost estimation:
400=$315
|  |  | 450=$340 |  |  | 90 | Graduates
[6 empty] | 20 | Approx. faculty, staff, & volunteers
[6 empty] | 470 | Attendance (roughly)
[6 empty] | TG Student Speakers: |  | General Student Speaker
[6 empty] | James Craig |  | Kandi Bauman
Aloni Greninger
Graduate Hooding Ceremony Locations:
[6 empty] | MES Hooding -- Recital Hall |  | 10:30 am-Pres/Provost @ 10:45
[6 empty] | MiT Hooding -- back of CRC |  | 10:00 am-Pres/Provost @ 10:15
[6 empty] | MPA Hooding -- Longhouse |  | 9:30 am-Pres/Provost @ 9:45

## Draft schedule
All times are Approximate
9:30 - 9:35 | Welcome | Tina Kuckkahn, JD
(Doreen will introduce Julie after Tina)
9:35 - 9:40 | Prayer | Julie Johnson/confirmed
9:40 - 9:45 | Introductions | Doreen will introduce Pres.& Provost
9:45 - 10:10 | Opening Remarks | President & Provost
10:10 - 10:15 | Student Speaker Introductions | Doreen
10:15 - 10:35 | Approx. 10 min. each cohort; TG has 2 student speakers both will keep it to 10 minutes (5 min./ea) | PNAPP: Kandi Bauman
TG: James Craig & Loni Greninger
10:35 - 11:30 (?) | Hooding commencement
11:30 | Closing Remarks | Doreen